## Log
Utility Correspondence Log (MOCK)
Reference | UTIL-EV-2026-00831 (mock)
Service address | Place (Palo Alto, CA) (mock)
Date | Channel | Subject | Outcome
2026-02-20 | Email | Confirm required attachments | Utility confirmed load letter + one-line + EMS brief (mock)
2026-02-21 | Portal | Submit application package | Submitted; awaiting review (mock)
2026-02-24 | Call | Pre-review: EMS questions | Utility requested monitoring + fail-safe clarification (mock)
2026-02-25 | Portal | Deficiency notice issued | Additional info required (mock)
2026-02-27 | Portal | Resubmit rework package | Resubmitted (mock)
2026-03-03 | Portal | Approval/acknowledgment | Approved/acknowledged (mock)