## ParsedLog
AHJ Comment Log (Parsed) (MOCK)
Application | EL-2026-01472 (mock)
Received | 2026-02-06
Comment ID | Location | Comment | Owner | Disposition/Response
C-01 | E-001 | Clarify EMS method/monitoring/fail-safe; cite code basis | Priya Shah, PE (mock) | Accepted; update one-line + notes
C-02 | E-001 | Provide fault current basis; confirm min AIC | Priya Shah, PE (mock) | Accepted; add fault basis note
C-03 | E-005 | Add continuous-load factor + labeling requirements | Priya Shah, PE (mock) | Accepted; expand notes
C-04 | E-002/E-004 | Standardize EVSP-1 designation across set | Sam Ortega (mock) | Accepted; update labels

## Summary
Summary (MOCK)
Total comments | 4
Open | 0
Resolved | 4
Resubmission target | 2026-02-12