## Log
Inspection Support Log (MOCK)
Application | EL-2026-01472 (mock)
Item | Question/Issue | Response Provided | Evidence | Status
IS-01 | Provide EMS cap confirmation for plan-check intent | Provided EMS configuration export showing cap set to 250A and fail-safe mode | P7.EMS_ConfigSummary_AsInstalled_2026-03-21.pdf | Closed
IS-02 | Confirm labeling/circuit IDs match drawings | Provided as-built schedule page and redline references | P7.FieldRedlines_Electrical_2026-03-18.pdf | Closed
IS-03 | Provide as-built record set for file | Issued as-built permit set (compiled) | P7.1_AsBuilt_ElectricalPermitSet_2026-03-22.pdf | Closed